## Slide 1: Outcome Study
Concept

## Slide 2: Outcome Studies - background
Many development projects share common features concerning Monitoring & Evaluation:
  The results-orientation of monitoring systems is often weak and not able to capture many outcomes and impacts
  Evaluators to carry out mid-term or final evaluations usually have very limited time to carry out their assignment. In addition:
    often evaluators are drowned in a large number of documents
    on the other hand they often spend a large part of their time collecting and collating data on outcomes and impacts and don't have sufficient time to analyze the data and work on conclusions and recommendations

## Slide 3: Outcome Studies - overview
How do Outcome Studies help in this situation?
  they condense all important information into a single (typically 20-40 page) report
  they partly rely on information collected through the projects' M&E system, but engage in further data-collection to address further information needs
    typically Stakeholder Interviews and Surveys with the target beneficiaries are carried out
    information needs are defined by project indicators and further main outputs, outcomes, impacts, sustainability, as identified through Results Models of key activities or working areas
  results are visualized as much as possible (e.g. by using charts)

## Slide 4: Step 1 – Define Information Needs understand indicators & establish results models
Usually an Outcome Study systematically follows up all indicators of the project
Why is further information usually required?
  Indicators usually don't comprehensively cover what the project tries to achieve
    certain areas of work might not be covered by indicators
    outputs, intermediate outcomes or impacts might within the same logical impact chain are not be covered by indicators, but are important to understand to comprehend strength and weaknesses of the projects' activities
What are Results Models?
  Results Models visualize the relationship between project activities, their Outputs, envisioned Outcomes and indicators in a simple manner and can furthermore show the attribution gap
  the project is structured into its key components, sub-components and key activities and their respective results logic and other cross-cutting issued are formulated
  they are the key tool to define, which information needs to be collected in the Outcome Study

## Slide 5: Step 2 – Define Data-Collection Tools
Based on the indicators and further data-items as defined through the results-model, data-collection tools are systematically defined
in order to do so, a matrix is created and for each data-item it is defined:
  through which data-collection tool it shall be monitored
  using which sampling (size and processes)
  which guide-questions

## Slide 6: Step 3 – Collect Data
According to experience, the 2 most common types of data-collection to be carried out are:
  Stakeholder interviews
    based on the identified guide-questions, those people are identified, who can best answer them
    a matrix is used as 'questionnaire', which shows all interviewees and all guide-questions and who will be asked what
  Surveys
    surveys might be useful to collection opinions, experiences and other information, mainly from (large-size) target groups
    in most cases, mixed method questionnaires (including qualitative and quantitative information and ratings) are used
    functional data-base tools and techniques to summarize/collate quantitative (by using charts) and qualitative (by categorization) information are available

## Slide 7: Step 4 – Data-Analysis & Reporting
with the developed tools, also large amounts of data can be analyzed / collected data does not 'get lost' on the way
Outcome Study reports summarize all information on key outputs, outcomes, impacts, sustainability and other cross-cutting issues in a single document
the findings are strongly based on the collected data
the report contains charts, tables and graphs in order to visualize the results and raise/sustain the interests by the reader

## Slide 8: Thank you!